Project Scope Statement I. General Information. Project name: Secure Multi-Site Network For SCG Hobby Project number: IT499-NET-001 Project Manager name: Christian Mclean Date: January 15, 2026 II. Project Overview. This project develops detailed planning documents for a secure multi-site network to connect four SCG Hobby locations. It addresses inefficient inventory/POS isolation and security risks by implementing WAN/VPN connectivity, upgraded local networks, and integrated physical security. The purpose is to enable unified, secure operations supporting current efficiency and future growth.. III. Project Goals and Objectives; - Specific & Measurable: Deliver complete conceptual/logical/physical designs, equipment recommendations, security policy, and phased implementation plan. - Agreed to & Realistic: Align with business needs via stakeholder input; use cost-effective Ubiquiti solutions. - Time Bound: Complete all deliverables within 8 weeks (by March 8, 2026). Success criteria: Approved documents enabling secure inter-site data sharing, centralized security monitoring, and scalability.. IV. Comprehensive List of Project Deliverables; - Conceptual and logical network designs (WAN/VPN topology, VLANs). - Physical design diagrams (floor plans with device/camera placements). - Equipment/vendor recommendations and cost breakdown ($20k–$30k range). - Security plan/policy (logical access, backups, physical integration). - Phased implementation plan (schedule, testing protocols, training outline). - Project archive/presentation materials. Critical Success Factors: Stakeholder approval, budget adherence, security integration, and scalability demonstrated in designs.. V. Comprehensive List of Project Requirements; - Site-to-site VPN/WAN using secure protocols (e.g., IPsec/WireGuard via Ubiquiti). - Managed PoE switches, Wi-Fi 6/7 APs, and IP PoE cameras (4–8 per site, 4K). - Centralized management software (UniFi). - Integration of alarms/sensors. - Compliance with basic security best practices (e.g., access controls, backups).. VI. Exclusions from Scope. - Actual hardware procurement or physical installation/implementation. - Ongoing maintenance/support contracts post-planning. - Custom software development (use off-the-shelf solutions). - Advanced enterprise features (e.g., full zero-trust beyond basic VPN).. VII. Time and Cost Estimates. Time: 8 weeks total (phased: Weeks 1–2 Initiation; 3–4 Planning/Conceptual; 5–6 Detailed Design; 7–8 Testing/Closing). Effort: 75–115 hours. Cost: $20,000–$30,000 preliminary hardware/essentials (low-end: ~$20k Ubiquiti-focused with 4 cameras/site; high-end: ~$30k with premium features).. VIII. Roles and Responsibilities. Role; Responsibilities. Project Manager; Overall coordination, documentation, reviews. Sponsor; Approval, business input, funding. Shop Managers; Site needs, floor plans, feedback. Technical Lead; Design/research, vendor recommendations.. IX. Assumptions; List all project assumptions.. - Stakeholders will provide timely input (e.g., site access/floor plans). - Ubiquiti ecosystem remains suitable and available. - No major regulatory changes affecting small business networks. - Internet service at sites supports VPN (adequate bandwidth).. X. Product Acceptance List all project acceptance criteria. Criteria. - All deliverables reviewed/approved by sponsor and stakeholders. - Designs support secure inter-site connectivity and physical integration. - Costs within $20k–$30k estimate; phased plan feasible in 8 weeks. - Documentation clear, professional, and ready for implementation phase.. XI. Constraints List all project constraints.. - Timeline: Must complete within 8 weeks (no critical date, but desired). - Budget: Preliminary cap at ~$30,000 for hardware planning. - Resources: Primarily planning-focused (limited to design/docs).. XII. Signatures Include signature lines for the project sponsor, project manager, key stakeholders, customers, and vendors..