Project Concept Document I. General Information. Project name: Secure Multi-Site Network for SCG Hobby Requestor name: Christian Mclean Requestor’s contact information: mcleanman36@yahoo.com; Project number: IT499-NET-001 Date of request:01/11/2025. Section One. II. Business Justification. SCG Hobby, a small business operating four local hobby shops in western Pennsylvania with about 20 employees, uses outdated networks at each site with no secure inter-site connectivity. This leads to inefficient inventory management, isolated POS systems, and vulnerability to theft/data breaches. As the company plans expansion potentially adding sites, without this project, risks include: - Operational silos causing stock discrepancies and lost sales. - Security gaps exposing customer data and physical assets. - Inability to scale securely for growth. - Higher costs from manual processes and potential losses. Approval will enable unified, secure operations across sites, support expansion via WAN/VPN, and integrate physical security like cameras/alarms.. III. Project Description. This project designs a secure network integrating LANs at four sites with WAN/VPN for inter-site connectivity, plus security policies including physical features cameras, alarms. High-level objectives and desired outcomes: - Deliver conceptual/logical and physical designs with WAN/VPN focus. - Recommend equipment, costs, and vendors. - Develop security plan/policy logical access, backups, plus physical integration like IP cameras/alarms. - Create phased implementation plan with schedule, testing, and training.. IV. Project Costs. - Core Networking WAN/VPN Focus - Site-to-site VPN routers/gateways Ubiquiti Dream Machine Pro/SE or similar per site, or central hub + branches: $500–$1,200 per site ×4 $2,000–$4,800 total. - Managed PoE switches for connecting devices, APs, cameras: $400–$1,000 per site $1,600–$4,000 total. - Wireless access points Wi-Fi 6/7 for in-store coverage: $150–$300 each 2–4 per site $1,200–$4,800 total. Subtotal: $4,800–$13,600 lower end favors Ubiquiti bundles for easier multi-site management. - Physical Security Integration Cameras + Alarms - IP PoE security cameras 4–8 per site, outdoor/indoor, 4K with night vision: $150–$500 each $2,400–$16,000 total aim for 5–6/site average. - NVR/recorder/storage central or cloud-hybrid, 4–8TB: $500–$2,000. - Alarm system basics sensors, control panel, siren per site: $500–$1,500 per site $2,000–$6,000 total. Subtotal: $4,900–$24,000 mid-range: ~$8,000–$12,000 for solid coverage without overkill. - Software/Licenses & Misc - UniFi/central management software often free/low-cost or advanced licenses: $0–$1,000. - VPN/security software add-ons if not built-in: $500–$1,500. - Cables, mounts, basic tools: $1,000–$2,000. Subtotal: $1,500–$4,500. Grand Total Estimate Hardware + Essentials: $20,000–$30,000 - Low end ~$20k: Budget-friendly Ubiquiti stack, minimal cameras 4/site, basic alarms. - High end ~$30k: More robust switches/APs, additional cameras 6–8/site, premium features like AI detection.. V. Timeframe; _____________. Is there a critical completion date? No Desired completion date: Within 8 weeks.

Project Concept Document—page 2 Section Two. VI. Planning Estimates. Phase; Duration; Key Tasks/Milestones; Estimated Effort. 1. Initiation & Requirements Gathering; Weeks 1–2 (Jan 12–25); - Define business goals/SMART objectives. - Gather/analyze user needs inventory sharing via WAN, camera feeds. - Initial stakeholder input virtual interviews with shop managers. - Complete Project Concept Document. Milestone: Approved concept & initial scope.; 15–25 hours total; focuses on high-level alignment.. 2. Planning & Conceptual Design; Weeks 3–4 (Jan 26–Feb 8); - Develop logical network design WAN/VPN topology, VLAN. - Outline security policy access controls, backups. - Research vendors/equipment Ubiquiti for VPN, IP cameras. - Create preliminary cost comparisons & risk list. Milestone: Conceptual diagrams & WBS draft.; 20–30 hours; iterative with research/tools.. 3. Detailed Design & Security Planning; Weeks 5–6 (Feb 9–22); - Finalize physical designs floor plans per site, camera/alarm placements. - Detail implementation plan phased rollout: site-by-site VPN setup, testing. - Refine security plan logical/physical integration, training outline. - Update WBS with subtasks/work packages. Milestone: Full designs, equipment list, & policy docs.; 25–35 hours; includes reviews/revisions.. 4. Monitoring, Testing Plans, & Closing; Weeks 7–8 (Feb 23–Mar 8); - Develop testing protocols, VPN connectivity, camera feeds. - Outline training & handover. - Compile all docs designs, plans, lessons learned. - Final reviews/adjustments. Milestone: Complete project archive & presentation prep.; 15–25 hours; ensures quality & closure.. Total estimated: 75–115 hours.. VII. Business Areas Impacted. - All shop locations (sales, inventory, management). - Employees (secure remote access for managers). - Expansion team (scalable infrastructure). - Customers (indirectly via better service/security).. Section Three — To be completed by the review committee. VIII. Selection Committee Review. Date of review: Comments: Project reviewed/denied: Project priority:. IX. Signatures of Review Committee.