## Sheet1
Risk Register
Secure Multi-Site Network for SCG Hobby
Project Number: IT499-NET-001
Date: March 6, 2026
Prepared by: Christian Mclean
Risk ID | Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Owner | Status (Final) | Residual Risk
R-01 | Missing or delayed floor plans from store managers | Medium | High | 12 | Follow-up calls + buffer in schedule; used placeholder diagrams until received | Christian Mclean | Closed | Low
R-02 | Budget exceeds $30,000 due to price changes | Low | High | 8 | Locked in 3-vendor comparison early; chose Ubiquiti for best value | Christian Mclean | Closed | Low
R-03 | Cloud backup integration adds unexpected complexity | Low | Medium | 6 | Added as approved change request; tested restore procedures | Logan Brown | Closed | Low
R-04 | Shop staff resistance to new security policies | Medium | Medium | 9 | Mandatory 2-hour training + simple policy language | Training Team | Closed | Low
R-05 | VPN connectivity failure during site rollout | Low | High | 8 | Built redundant testing scripts and failover plan | Aaron Schriber | Closed | Low
R-06 | UniFi hardware availability delays | Low | Medium | 6 | Ordered early with lead time buffer | Christian Mclean | Closed | Low
Overall Project Risk Level at Close: Low