Revised Full Physical Implementation Plan & Gantt Chart
Secure Multi-Site Network for SCG Hobby
Project #: IT499-NET-001

Prepared by: Christian Mclean

Date: March 8, 2026

This document is the planned future rollout schedule that will begin immediately after the current planning project ends on March 8, 2026. The 8-week planning phase (Jan 20 – Mar 8) is now complete.

Proposed Physical Implementation Timeline

| Phase / Task | Start Date | Duration | End Date | Owner | Key Deliverables / Notes |
| --- | --- | --- | --- | --- | --- |
| Phase 0: Procurement & Prep | Mar 9, 2026 | 7 days | Mar 17, 2026 | Christian Mclean | Order all equipment, schedule install dates |
| Phase 1: Site 1 Rollout | Mar 18, 2026 | 7 days | Mar 26, 2026 | Logan Brown | Full install + configuration |
| VPN & VLAN Configuration | Mar 20, 2026 | 2 days | Mar 22, 2026 | Aaron Schriber | Site-to-site VPN live |
| Testing & Validation | Mar 23, 2026 | 3 days | Mar 26, 2026 | Aaron Schriber | Connectivity, cameras, POS sync, cloud backup test |
| Staff Training (2 hrs) | Mar 26, 2026 | 1 day | Mar 26, 2026 | Training Team | UniFi dashboard + alarm system |
| Phase 2: Site 2 Rollout | Mar 30, 2026 | 7 days | Apr 7, 2026 | Logan Brown | Repeat process |
| Phase 3: Site 3 Rollout | Apr 13, 2026 | 7 days | Apr 21, 2026 | Logan Brown | Repeat process |
| Phase 4: Site 4 Rollout | Apr 27, 2026 | 7 days | May 5, 2026 | Logan Brown | Repeat process |
| Phase 5: Full System Testing | May 6, 2026 | 5 days | May 12, 2026 | Aaron Schriber | End-to-end testing across all 4 sites |
| Phase 6: Final Training & Handover | May 13, 2026 | 3 days | May 16, 2026 | Training Team | Final training + signed handover checklist |
| Project Closeout | May 16, 2026 | 1 day | May 16, 2026 | Christian Mclean | Final documentation delivered |